## Sheet1
Tasks |  | Task Allocation | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Discovery
1 | Sponsor Meeting | ALL | bar: Week 0
2 | Business Problem Discovery | ALL | bar: Week 0
Proposal Submission | [19 empty] | LEGEND
3 | Proposal Document | Shafiq | bar: Week 1
4 | Wiki Page | Edwin | bar: Week 1
Milestone 1: Project Proposal Submission | [19 empty] | RED | Milestone
Data Preparation
5 | Signing of NDA | ALL | [17 empty] | BLUE | Intermediate Goals | bar: Week 2
6 | Gathering Data from Sponsor | ALL | bar: Week 2
7 | Exploratory Data Analysis (EDA) | Edwin | [17 empty] | ✓ | Completed | bar: Week 3
8 | Data Integration (Hard to soft copy) | ALL | bar: Week 3 to Week 5
9 | Data Cleaning | Shafiq | [17 empty] | ✓ | Proposed (Subject to changes) | bar: Week 5 to Week 6
10 | Data Processing | Shafiq | bar: Week 6 to Week 7
11 | Data Visualization and Findings | Edwin | bar: Week 6 to Week 7
Sponsor and Supervisor Review
12 | Review Data Findings | ALL | bar: Week 6 to Week 7
13 | Finalise Project Objectives and Scope | ALL | bar: Week 6 to Week 7
Interim
14 | Interim Wiki Page | Edwin | bar: Week 7 to Week 8
15 | Interim Presentation Slides | Shafiq | bar: Week 7 to Week 8
16 | Interim Project Review with Sponsor | ALL | bar: Week 7 to Week 8
Milestone 2: Interim Project Deliverables
17 | Business Problem Solution Research | Shafiq | bar: Week 9 to Week 10
18 | Model Planning | Edwin | bar: Week 10 to Week 11
19 | Initial Modelling Process | ALL | bar: Week 11
20 | Building Analytical Model (Full Scale Solution) | ALL | bar: Week 11 to Week 12
Sponsor and Supervisor Review
21 | Review Model with Supervisor and Sponsor | ALL | bar: Week 12
22 | Model Changes (if any) | ALL | bar: Week 13
23 | Finalise Model | ALL | bar: Week 13
Final Preparation
24 | Update Final Wiki Page | Edwin | bar: Week 14 to Week 16
25 | Prepare Final Presentation Slides | Shafiq | bar: Week 14 to Week 16
26 | Prepare Final Poster | Edwin | bar: Week 14 to Week 16
27 | Prepare Conference Paper | ALL | bar: Week 14 to Week 16
28 | Final Project Review with Sponsor | ALL | bar: Week 14 to Week 16
Milestone 3: Final Project Deliverables